# MULTIPLE PI LEADERSHIP PLAN

The EMBRACE (Elder Mistreatment: Building a Repository for Accessible and Comprehensive Evidence) project will be led by Dr. Brad Cannell and Dr. Shayan Shams as multiple principal investigators. This leadership structure ensures that the project benefits from their complementary expertise in elder mistreatment research, biomedical informatics, and data science. The responsibilities of the two PIs have been clearly delineated to maximize project efficiency, ensure scientific rigor, and foster innovation. Below, we outline the roles and responsibilities of each PI and how they will collaborate to ensure the success of the project.

# A. Governance and Organization Structure of the Leadership Team

The governance and organizational structure of the EMBRACE leadership team is designed to ensure clear communication, efficient decision-making, and shared accountability. Dr. Brad Cannell, as the Contact Principal Investigator (PI), will lead the scientific, fiduciary, and operational aspects of the project, ensuring compliance with institutional and funding requirements, while Dr. Shayan Shams will provide leadership on the technical development and data security aspects of the project. Both PIs will collaborate closely on strategic decisions related to project planning, timelines, and resource allocation. Further, the MPIs will share responsibility for ensuring that systems are in place to guarantee institutional compliance with US laws, DHHS and NIH policies including human research, and data sharing.

Regular weekly meetings will be held to facilitate ongoing communication between the PIs and the broader project team, allowing for real-time problem solving and alignment of project goals. In addition to these meetings, an external advisory committee comprising stakeholders and experts in elder mistreatment and data science will be consulted periodically to provide input on project progress, challenges, and improvements. The governance structure is further supported by well-defined roles for each PI, enabling a clear division of responsibilities while ensuring joint decision-making for key project milestones. This structure ensures that the leadership team remains agile, accountable, and responsive to both project demands and stakeholder needs.

# B. Communication Plans

The leadership team will maintain frequent and open communication to ensure seamless collaboration and the alignment of scientific, technical, and operational objectives. Weekly team meetings will be scheduled to discuss project progress, address challenges, and make key decisions regarding the project’s direction. Dr. Cannell, as the contact PI, will facilitate these meetings, and be primarily responsible for communication with NIH, including the submission of annual reports.

# C. Process for Decisions on Scientific Direction

The MPIs have jointly and equitably contributed to the development of the proposed study. To date, decisions about the scientific direction of the proposed study have been made jointly, in consultation with the co-investigators. Therefore, both Dr. Cannell and Dr. Shams will continue to share decision-making responsibilities for scientific direction, resource allocation, and project timelines, with each PI contributing based on their respective areas of expertise.

# D. Procedures for Resolving Conflicts

While Dr. Cannell and Dr. Shams share complementary skills and a strong collaborative relationship, potential conflicts will be addressed proactively. In the unlikely event of a disagreement, both PIs will work together to find a consensus. If they fail to develop a strategy to deal with a problem, they will seek assistance from the project co-investigators. If necessary, they may also consult with senior leadership at UTHealth Houston to facilitate resolution. In the unlikely event that the problem is not resolved with the assistance of the co-investigators and senior leadership, it will be referred to an arbitration committee consisting of at least one impartial senior executive from the School of Public Health, and one impartial senior executive from the McWilliams School of Biomedical Informatics. No members of the arbitration committee will be directly involved in the project or with the problem area. Additionally, authorship of publications that result from this project will be based on the relative scientific contributions to the research and each manuscript.

# E. Leadership Roles and Responsibilities

Dr. Brad Cannell (Contact PI)

Dr. Cannell will serve as the Contact Principal Investigator and provide overall fiduciary, scientific, and operational oversight for the EMBRACE project. Dr. Cannell is an associate professor with appointments across three schools at the University of Texas Health Science Center at Houston (UTHealth Houston), giving him a unique interdisciplinary perspective on both the research and management aspects of the project. His specific responsibilities include:

- Project Oversight: Dr. Cannell will oversee all aspects of project operations, including the extensive planning, supervision of staff and graduate students, and analysis and reporting activities.

- Fiduciary Oversight: He will be responsible for ensuring compliance with all fiduciary regulations, submitting periodic reports, and overseeing the project budget.

- Scientific Leadership: Dr. Cannell will contribute his expertise in elder mistreatment and aging research to ensure the scientific integrity and relevance of the project.

- Coordination with Agencies: He will coordinate project activities with external stakeholders, ensuring strong collaboration between UTHealth Houston and other involved agencies.

- Training and Development: Dr. Cannell will oversee the development of materials, provision of services, and training for project staff, ensuring that the project team has the skills and resources necessary to execute the project plan effectively.

Dr. Shayan Shams

Dr. Shams, an assistant professor at the McWilliams School of Biomedical Informatics and the Institute for Stroke and Cerebrovascular Diseases at UTHealth Houston, brings significant expertise in artificial intelligence, big data, image and signal processing, and data privacy. His primary responsibilities will focus on the technical and computational aspects of EMBRACE. Specific responsibilities include:

- Technical Oversight: Dr. Shams will direct the technical aspects of creating and maintaining the data repository, ensuring the repository is robust, scalable, and secure.

- Data Privacy and Security: He will lead efforts to develop and implement protocols for data privacy and security, ensuring that the repository adheres to all relevant regulations and best practices for protecting sensitive information.

- Data Dashboard Development: Dr. Shams will oversee the development of AI-assisted data dashboards, ensuring they are user-friendly, intuitive, and capable of facilitating meaningful data exploration and analysis.

- Collaborative Planning: He will collaborate closely with Dr. Cannell in the development of the project plan, budget, and schedules, and will assist in monitoring the progress of the project to identify and resolve any technical challenges.